## SOFTWARE
SOFTWARE
No. | TITLE | ACTIVITIES | TARGET DATE | ACCOMPLISHED | REMARKS
1 | Crud for the admin side (BACKEND) | Back End (Admin Social Media) Posting of Announcements, events and news. | 2018-01-15
2 | Crud for the admin side (BACKEND) | Back End (Admin) Handling Student , Professor and Registrar | 2018-01-22
3 | Model Relationship and Crud for Admin Side | Back End (Admin, Registrar) Creating of classroom | 2018-01-29
4 | Model Relationship | Back End (Admin, Registrar) Creating of classroom | 2018-02-05
* Interview to the admin for data gathering
5 | Project Hosting | Design the Interface and Hosting of the System | 2018-02-12
6 | Model Relationship and CRUD for Admnin Side | Front end for Proffessor, Student and Admin side | 2018-02-19
7 | Multiple Authentication | System Security | 2018-02-26
8 | Testing | Testing of the system | 2018-03-05
9 | Solving | Solving bugs and errors of the system | 2018-03-12
10 | System Review | Review system functions, interface and methods | 2018-03-18

## DOCUMENTS
DOCUMENT
No. | TITLE | ACTIVITIES | TARGET DATE | ACCOMPLISHED | REMARKS
1 | Chapter III | Completion of Literature and Studies | 2018-01-15
2 | Chapter I to II | Revision of Chapter I, II | 2018-01-22
3 | Chapter III | Revision of Chapter III | 2018-01-29
4 | Chapter IV | Submission of Status of the Current System, Replacing, Problems | 2018-02-05
5 | Chapter IV | Submission of Terms of Processing, Basic Features, Acceptability | 2018-02-12
6 | Chapter V | Submission of Summary, Conclusions, Recommendations and Bibliography | 2018-02-19
7 | Chapter V | Full revision of chapter IV and V Topics | 2018-02-26
8 | Completion | Submission of appendices, curriculum vitae and list of figures | 2018-03-05
9 | Chapter I to V | Review of Chapter I to V | 2018-03-12
10 | Chapter I to V | Submission of Chapter I to V hard copy | 2018-03-18

## Sheet1 (hidden)
SOFTWARE
DATE |  | Activities | Target | Accomplished | REMARKS
2018-01-15 | 1 | Create, Read, Update, Delete | Back End (Admin Social Media) Posting of Announcements, events and news.
2018-01-22 | 2 | Create, Read, Update, Delete | Back End (Admin) Handling Student , Professor and Registrar
2018-01-29 | 3 | Model Relationship and CRUD | Back End (Admin, Registrar) Creating of classroom
2018-02-05 | 4 | Model Relationship | Back End (Admin) Assigning of classroom and subject to the Professor
2018-02-12 | 5 | Model Relationship and CRUD | Front End (Professor side) Grading
2018-02-19 | 6 | Hosting and Design the Interface | Design interface and Hosting
2018-02-26 | 7 | File Uploading for Professor | Front End (Prof side) File Uploading
2018-03-05 | 8 | Multiple Authentication | Security of the system
2018-03-12 | 9 | Review | Review the interface and review funtion and methods
2018-03-18 | 10 | Testing of the system | Testing the whole system
DOCUMENTS
DATE |  | Activities | Target | Accomplished | REMARKS
2018-01-15 | 1 | Completion of Literatures and Studies | Completion of Literatures and Studies
2018-01-22 | 2 | Revision of Chapter 1 to 3 | Revision of Chapter 1 to 3
2018-01-29 | 3 | Submission of Chapter 4 | Status of Current System, Replacing, Problems
2018-02-05 | 4 | Submission of Chapter 4 | Terms of Processing, Basic Features, Acceptability
2018-02-12 | 5 | Revision of Chapter 4 | Full revision of chapter 4 topics
2018-02-19 | 6 | Submission of Chapter 5 | Summary, Conclusions, Recommendations and Bibliography
2018-02-26 | 7 | Revision of Chapter 5 | Full revision of chapter 5 topics
2018-03-05 | 8 | Appendices | Submission of appendices, curriculum vitae and list of figures
2018-03-12 | 9 | Submission of Chapter 1 to 5 | Submission of Chapter 1 to 5
2018-03-18 | 10 | Review of Chapter 1 to 5 | Review of Chapter 1 to 5

## Sheet2 (hidden)
SOFTWARE | 2018-01-15
| Target | Accomplished
Activities
1 | Back End (Admin) Posting of Announcements, events and news.
Crud of announcements
Crud of events
Crud of news.